## Activity.WorkBreakdownStructure
WBS ID | Level | Task/Work Package Name | Duration | Dependencies (WBS ID & Name) | DAVID DOMINGUEZ
1 |  | Portfolio Website (Deliverable) | 12 days |  | CIS 4860
1.1 | Work Package | Project Plan Development | 2 days total
1.1.1 | Task | Gather requirements | 2 days
1.1.2 | Task | Identify stakeholders | 1 day
1.1.3 | Task | Risk assesment | 1 day
1.1.4 | Task | Define scope | 1 day
1.1.5 | Task | Set milestones | 1 day
1.1.6 | Task | Develop Budget | 1 day
1.1.7 | Task | Approval of plan | 1 day
1.2 | Work Package | Design & Mockups | 2 days total
1.2.1 | Task | Design for all 5 sections (Home, About, Portfolio, Resume, Contact) | 1 day
1.2.2 | Task | Sketch initial design | 2 days
1.2.3 | Task | Create wireframe | 2 days
1.2.4 | Task | Design visual elements | 1 day
1.3 | Work Package | Feedback Cycle | 1 day total | 1.3 ¦¦ 1.2
1.3.1 | Task | Review and incorporate feedback | 1 day
1.3.2 | Task | Conduct design review | 1 day
1.3.3 | Task | Gather feedback | 1 day
1.3.4 | Task | Implement changes | 1 day
1.4 | Work Package | Content Development | 2 days total | 1.4 ¦¦ 1.2
1.4.1 | Task | Draft for all sections (Home, About, Portfolio, Resume, Contact) | 2 days
1.4.2 | Task | Content development for networking/sysadmin work samples | 1 day
1.4.3 | Task | Finalize content | 1 day
1.5 | Work Package | Website Development | 5 days total | 1.5 ¦¦ 1.4
1.5.1 | Task | Technical Development | 5 days
1.5.2 | Task | Code homepage | 5 days
1.5.3 | Task | Setup development environment | 2 days
1.5.4 | Task | Launch website | 2 days
1.6 | Work Package | Feedback Cycle | 1 day total | 1.6 ¦¦ 1.5
1.6.1 | Task | Review and incorporate feedback | 1 day
1.6.2 | Task | Conduct design review | 1 day
1.6.3 | Task | Gather feedback | 1 day
1.6.4 | Task | Implement changes | 1 day
2 |  | Job application campaign | 7 days
2.1 | Work Package | Apply to 15 networking/sysadmin positions with URL included in application | 7 days total | 2.1 ¦¦ 1.6
2.1.1 | Task | Track spreadsheet showing company/position/date/response | 1 day
3 |  | Interview Preparation Package | 7 days
3.1 | Work Package | Talking points for each portfolio project within 2 weeks. | 7 days total
3.1.1 | Task | 1 page work samples summary sheet ready for interviews | 7 days
4 |  | Networking Professional Outreach | 5 days
4.1 | Work Package | Share portfolio with 10 industry professionals( professors, mentors, almunis, LinkedIn connections) | 5 days total | 4.1 ¦¦ 1.5
4.1.1 | Task | Request feedback withing 3 weeks of launch | 5 days
4.1.2 | Task | Document feedback | 1 day
5 |  | Launch & Stakeholder validation | 21 days
5.1 | Work Package | Gather usability/content feedback from 3 stakeholders | 21 days total
5.1.1 | Task | Track and follow up job on applications | 21 days